## Sheet1
Number | Level | Description | Estimate (Hours)
1 | Initiative | Establish Framework | 5
1.1 | Epic | Node.js application with SQLite backend | 5
1.1.1 | Feature | Set up Node.js environment | 3
1.1.1.1 | Story | Install required packages and dependencies | 2
1.1.1.2 | Story | Configure server settings | 1
1.1.2 | Feature | Logging via Winston | 2
1.1.2.1 | Story | Set up Winston for local file logging | 2
2 | Initiative | Design Data Models | 12
2.1 | Epic | Design user model | 2
2.1.1 | Feature | Define user schema | 2
2.1.1.1 | Story | Define user attributes and relationships | 2
2.2 | Epic | Design role/skill/subskill model | 10
2.2.1 | Feature | Define role/skill/subskill schema | 4
2.2.1.1 | Story | Define role/skill/subskill attributes and relationships | 4
2.2.2 | Feature | Data mine ChatGPT for roles, skills, subskills, and questions | 6
2.2.2.1 | Story | Identify 5 sample roles | 3
2.2.2.2 | Story | Identify corresponding skills, subskills, and questions | 3
3 | Initiative | Build Node Basic Functionality | 34
3.1 | Epic | Implement models in the database | 6
3.1.1 | Feature | Create user model in the database | 2
3.1.1.1 | Story | Define user table and relations in SQLite | 2
3.1.2 | Feature | Create role/skill/subskill model in the database | 4
3.1.2.1 | Story | Define role/skill/subskill table and relations in SQLite | 4
3.2 | Epic | Develop UI for role and expertise input | 8
3.2.1 | Feature | Create a conversation page with ChatGPT API | 8
3.2.1.1 | Story | Design UI for user interaction | 4
3.2.1.2 | Story | Integrate ChatGPT API for conversation | 4
3.3 | Epic | Generate role breakdown and save to database | 8
3.3.1 | Feature | Retrieve role breakdown from ChatGPT | 4
3.3.1.1 | Story | Fetch skills, knowledge, and competencies from ChatGPT API | 4
3.3.2 | Feature | Save role breakdown to database | 4
3.3.2.1 | Story | Insert role breakdown data into SQLite | 4
3.4 | Epic | Develop test and result handling | 12
3.4.1 | Feature | Design test result data model | 2
3.4.1.1 | Story | Define test result attributes and relationships | 2
3.4.2 | Feature | Build test-taking functionality | 7
3.4.2.1 | Story | Develop function to select 15 questions | 3
3.4.2.2 | Story | Design UI for test-taking | 2
3.4.2.3 | Story | Implement result tracking during testing | 2
3.4.3 | Feature | Save test results in the database | 2
3.4.3.1 | Story | Insert test result data into SQLite | 2
3.4.4 | Feature | Analyze results and compare to competencies | 6
3.4.4.1 | Story | Compare test results to expected competencies | 3
3.4.4.2 | Story | Generate competency-based analysis | 3
3.4.5 | Feature | Develop UI for result display | 6
3.4.5.1 | Story | Design UI for displaying test results and analysis | 3
3.4.5.2 | Story | Integrate result display UI with the analysis module | 3
4 | Initiative | Creating a Personalized Training and Development Plan | 18
4.1 | Epic | Build tailored development plan for each employee | 10
4.1.1 | Feature | Identify employee's strengths and weaknesses | 4
4.1.1.1 | Story | Analyze test results and experience to determine strengths and weaknesses | 4
4.1.2 | Feature | Generate a personalized development plan | 6
4.1.2.1 | Story | Develop algorithm to create a plan based on identified strengths and weaknesses | 3
4.1.2.2 | Story | Design UI for displaying the development plan | 3
4.2 | Epic | Incorporate industry experience into the plan | 8
4.2.1 | Feature | Research industry trends and best practices | 4
4.2.1.1 | Story | Identify relevant trends and practices for each role | 4
4.2.2 | Feature | Integrate industry experience into the development plan | 4
4.2.2.1 | Story | Update the development plan algorithm to consider industry experience | 4
5 | Initiative | Include Employment History | 16
5.1 | Epic | Auto read resume to update experience | 16
5.1.1 | Feature | Parse employment history from resume | 4
5.1.1.1 | Story | Develop algorithm to extract employment history from resume | 2
5.1.1.2 | Story | Test resume parsing with different resume formats | 2
5.1.2 | Feature | Update user schema and insert parsed employment history | 6
5.1.2.1 | Story | Modify user schema to include employment history attributes | 3
5.1.2.2 | Story | Insert parsed employment history into SQLite database | 3